## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Alex Cherry | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check main functionality developed
Main functionality of Application |  |  |  | Visual Studio 2015 (professional/community) Visual Studio 2017 (professional/community) Visual Studio 2019 (professional/community) Android/UWP/iOS
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Age/Name booleans working | Main functionality | 1. Head to main page 2. Enter details into name textbox 3. Enter details into age textbox | When Enter Info button is clicked, all other buttons become active | Buttons become available to click | Buttons become available to click | Pass |  | Works as intended
2 | 1 | TC.002 | Game 1 functionality | Main functionality | 1. Head to main page 2. Head to Game 1 page 3. Play Game | Counter works and game displays correct number of clicks | Game 1 works perfectly | Game 1 works perfectly | Pass |  | Works as intended
3 | 1 | TC.003 | Game 2 functionality | Main functionality | 1. Head to main page 2. Head to Game 2 page 3. Play Game | Timer works and text validation works | Game 12works perfectly | Game 2 works perfectly | Pass |  | Works as intended
4 | 1 | TC.004 | Game 3 functionality | Main functionality | 1. Head to main page 2. Head to Game 3 page 3. Play Game | Timer works and random time for button to appear works | Game 3 works perfectly | Game 3 works almost perfectly, first button click displays a null value but second makes game work correctly | Pass |  | Small bug, no big issues as game still functions correctly
5 | 1 | TC.005 | Platform Checker | Android Functionality | 1. Load up VS and try run from Device | Check If Xamarin.Forms loads on mobile device | Runs on Device | Error message saying could not find device. Please connect one. | Fail | Defect No1, Priority = Minor Severity = Minor | Try connect device properly

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%